## Prioritization All Projects
Order | Project Information | [6 empty] | Benefit Score | [10 empty] | Cost Score |  | Cost Benefit | Feasibility Designation |  | Climate Change
| Rank | Project Name | Geomorphic Sub Reach | Project Type | Downstream RM | Upstream RM | Total Length (mi) | Restoration Gap Analysis |  |  |  | Existing and Potential Fish Use |  | Root Causes |  | Ecological Concerns |  | Total Benefit Score | Score (1-3) | Rationale/ Assumptions | Benefit to Cost Score | Feasibility Designation | Rationale/ Assumptions | Climate Change Designation | Rationale/Assumptions
[8 empty] | Existing Condition (1-7) | Achievable Target (1-7) | Final Gap Score Target - Existing (0-6) | Rationale/Assumptions | Score (1-3) | Rationale/Assumptions | Score (1-3) | Rationale/Assumptions | Score (1-3) | Rationale/Assumptions
18 | 1 | LBC Project Area 6 | LBC reach 3 | Instream and Floodplain Restoration | 3 | 5.1 | 2.1 | 3 | 6 | 3 | moderate existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 3 | Mostly process restoration to address root causes | 3 | addresses side channel and wetland habitat conditions, instream structural complexity, and bed and channel form and riparian condition; actions to increase floodplain groundwater storage may modestly address water quantity and temperature | 12 | 2 | relatively easy access and typical restoration techniques | 6 | High | public ownership, no know issues limiting project feasibility | High | side channels, alcoves, wetland and riparian restoration can ameliorate temperate and peak flow increases and increase salmon resilience
28 | 2 | Beaver Management | LBC Reaches 2 and 3 | Beaver Management | 0.7 | 5.1 | 4.4 | 3 | 5 | 2 | low to moderate current conditions, moderate to high recovery potential | 3 | high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 3 | process restoration addressing root causes (beaver extirpation) | 3 | addresses water quantity, water temperature, side channel and wetland habitat conditions | 11 | 1 | relatively low cost, availability for volunteer labor | 11 | High | Mostly public land ownership; existing programs in the subbasin for reintroducing beavers | High | beaver activity can ameliorate temperate and peak flow increases and increase salmon resilience
2 | 3 | UTR Project Area 2 | UTR Reach 2a | Instream and Floodplain Restoration | 20.1 | 20.9 | 0.8 | 4 | 6 | 2 | moderate-to-high existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | productive area for multiple target species spawning (steelhead and Chinook) rearing (steelhead, Chinook and bull trout) | 3 | Mostly process restoration to address root causes | 3 | addresses side channel and wetland habitat conditions, instream structural complexity, bed and channel form, and riparian condition | 11 | 2 | relatively easy access and typical restoration techniques | 5.5 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
5 | 4 | UTR Project Area 5 | UTR Reach 2d | Instream and Floodplain Restoration | 22.4 | 22.7 | 0.3 | 4 | 6 | 2 | moderate-to-high existing ecosystem function and habitat quality; High ecosystem function and habitat quality assuming all proposed actions implemented | 3 | productive area for multiple target species spawning (steelhead and Chinook) rearing (steelhead, Chinook and bull trout) | 3 | Mostly process restoration to address root causes | 3 | addresses side channel and wetland habitat conditions, instream structural complexity, bed and channel form | 11 | 2 | moderately difficult access; relatively limited instream work and typical restoration techniques | 5.5 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
8 | 5 | UTR Project Area 8 | UTR Reach 3c | Instream and Floodplain Restoration | 24.8 | 25.5 | 0.7 | 5 | 6 | 1 | moderate-to-high existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | productive area for multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 3 | Mostly process restoration to address root causes | 3 | addresses side channel and wetland habitat conditions, instream structural complexity, bed and channel form | 10 | 2 | moderately difficult access; moderate instream work with typical restoration techniques | 5 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
11 | 6 | UTR Project Area 11 | UTR Reach 5 | Instream and Floodplain Restoration | 27.5 | 28 | 0.5 | 5 | 6 | 1 | moderate to high existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | productive area for multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 3 | Mostly process restoration to address root causes | 3 | addresses side channel and wetland habitat conditions, instream structural complexity, and bed and channel form | 10 | 2 | moderately difficult access; moderate amount of instream work with typical restoration techniques | 5 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
13 | 7 | LBC Project Area 1 | LBC Reach 1 | Instream and Floodplain Restoration | 0 | 0.7 | 0.7 | 2 | 5 | 3 | low existing ecosystem function and habitat quality; moderate to high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | moderate to high potential productivity multiple target species spawning and rearing (steelhead and bull trout); Chinook rearing near mouth | 2 | mix of process restoration and habitat enhancement | 2 | addresses instream structural complexity, bed and channel form, riparian condition, and increased sediment quantity | 10 | 2 | easy to moderately difficult access and moderate amount of instream work with typical restoration techniques | 5 | Moderate | multiple private landowners affected (lower 0.2 miles), their willingness is unknown | Low | low potential for ameliorating impacts or increasing resilience
3 | 8 | UTR Project Area 3 | UTR Reach 2b | Instream and Floodplain Restoration | 20.9 | 21.6 | 0.7 | 4 | 6 | 2 | moderate-to-high existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | productive area for multiple target species spawning (steelhead and Chinook) rearing (steelhead, Chinook and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses side channel and wetland habitat conditions, instream structural complexity | 9 | 2 | moderately difficult access; relatively limited instream work and typical restoration techniques | 4.5 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
4 | 9 | UTR Project Area 4 | UTR Reach 2c | Instream and Floodplain Restoration | 21.8 | 22.2 | 0.4 | 4 | 6 | 2 | moderate-to-high existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming removal of all infrastructure in the floodplain | 3 | productive area for multiple target species spawning (steelhead and Chinook) rearing (steelhead, Chinook and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses instream structural complexity, bed and channel form | 9 | 2 | relatively easy access and typical restoration techniques; potential road decommissioning with low to moderate amount of floodplain fill removal | 4.5 | Moderate | public ownership; road decommissioning impacts access for recreation, fire suppression, and other uses | Low | low potential for ameliorating impacts or increasing resilience
9 | 10 | UTR Project Area 9 | UTR Reach 3d | Instream and Floodplain Restoration | 26 | 26.4 | 0.4 | 5 | 6 | 1 | moderate-to-high existing ecosystem function and habitat quality; High ecosystem function and habitat quality assuming removal of all infrastructure in the floodplain | 3 | productive area for multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 2 | mix of process restoration and habitat enhancement | 3 | addresses side channel and wetland habitat conditions, instream structural complexity, bed and channel form, riparian condition, and increased sediment quantity | 9 | 2 | easy access, moderate amount of instream work; come alternatives to realign road could increase to high cost | 4.5 | Moderate | public ownership; proposed actions may impact recreational areas | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
17 | 11 | LBC Project Area 5 | LBC Reach 2d | Instream and Floodplain Restoration | 2.1 | 3 | 0.9 | 3 | 5 | 2 | moderate existing ecosystem function and habitat quality; moderate to high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | high potential productivity multiple target species spawning and rearing (steelhead and bull trout)mouth | 2 | mix of process restoration and habitat enhancement | 2 | addresses side channel and wetland habitat conditions, instream structural complexity, and bed and channel form, and riparian condition | 9 | 2 | relatively easy access, relatively limited instream work and typical restoration techniques | 4.5 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
1 | 12 | UTR Project Area 1 | UTR Reach 1 | Instream and Floodplain Restoration | 17.8 | 18.2 | 0.4 | 5 | 6 | 1 | moderate-to-high existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming removal of all infrastructure in the floodplain | 3 | highly productive area for multiple target species spawning (steelhead and Chinook) rearing (steelhead, Chinook and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses side channel and wetland habitat conditions instream structural complexity | 8 | 2 | easy access, relatively limited instream work; potential road decommissioning with moderate amount of floodplain fill removal | 4 | Moderate | Public ownership; road decommissioning impacts access for recreation, fire suppression, and other uses | Low | floodplain fill removal would improve side channel habitat but low potential for ameliorating impacts or increasing resilience
6 | 13 | UTR Project Area 6 | UTR Reach 3a | Instream and Floodplain Restoration | 23.5 | 23.7 | 0.2 | 5 | 6 | 1 | moderate-to-high existing ecosystem function and habitat quality; high ecosystem function assuming all proposed actions implemented | 3 | productive area for multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses side channel and wetland habitat conditions, instream structural complexity | 8 | 2 | moderately difficult access; relatively limited instream work and typical restoration techniques | 4 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
15 | 14 | LBC Project Area 3 | LBC Reach 2b | Instream and Floodplain Restoration | 1 | 1.7 | 0.7 | 4 | 5 | 1 | moderate to high existing ecosystem function and habitat quality; moderate to high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses instream structural complexity, riparian condition, and increased sediment quantity | 8 | 2 | moderately difficult access; relatively limited instream work and typical restoration techniques | 4 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience
24 | 15 | War Creek | WC Reach 1 | Instream and Floodplain Restoration | 0.3 | 1.3 | 1 | 4 | 5 | 1 | moderate to high existing ecosystem function and habitat quality (downstream of RM 0.3 to 0.7); moderate to high ecosystem function and habitat quality assuming all project actions implemented | 2 | multiple target species spawning (possible steelhead; possible Chinook lower 0.2 miles) and rearing (Chinook lower 0.3 miles, steelhead, and bull trout) | 3 | Mostly process restoration to address root causes | 2 | Addresses bed and channel form | 8 | 2 | easy access, relatively little instream work and typical restoration techniques | 4 | Moderate | Public ownership; road decommissioning impacts access for recreation, fire suppression, and other uses | Low | low potential for ameliorating impacts or increasing resilience
26 | 16 | Canyon Creek | CC Reach 1 | Instream and Floodplain Restoration | 0 | 0.4 | 0.4 | 2 | 4 | 2 | low existing ecosystem function and habitat quality; moderate to high ecosystem function and habitat quality assuming all proposed actions implemented | 1 | potential for steelhead rearing; barrier currently blocks upstream migration | 3 | Mostly process restoration to address root causes | 2 | addresses instream structural complexity, riparian condition, and increased sediment quantity | 8 | 2 | Easy access and minimal instream work; relatively high cost for the Twisp River road crossing | 4 | Moderate | multiple private landowners affected (lower 0.2 miles), their willingness is unknown | Low | low potential for ameliorating impacts or increasing resilience
27 | 17 | Land Acquisition | CC Reach 1 and LBC Reach 1 | Land Acquisition | N/A | N/A | N/A | 3 | 5 | 2 | Implementing introduced species management has the potential to improve ecosystem function and habitat quality | 3 | for LBC, high potential productivity multiple target species spawning and rearing (steelhead and bull trout); Chinook rearing near mouth | 2 | partial restoration of root causes (land use impacts) | 1 | does not directly address limiting factors | 8 | 2 | moderate cost relative to instream restoration; could be low cost if not all parcels are purchased | 4 | Moderate | moderate feasibility due to unknown landowner willingness | Low | low potential for ameliorating impacts or increasing resilience
23 | 18 | Reynolds Creek | RC Reach 1 | Instream and Floodplain Restoration | 0 | 0.6 | 0.6 | 4 | 4 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 2 | multiple target species spawning (bull trout) and rearing (possibly Chinook, steelhead, and bull trout) | 3 | Mostly process restoration to address root causes | 2 | Addresses bed and channel form | 7 | 1 | easy access, no instream work, potential road decommissioning relatively inexpensive compared to typical restoration techniques | 7 | Moderate | Public ownership; road decommissioning impacts access for recreation, fire suppression, and other uses | Low | low potential for ameliorating impacts and increasing resilience
25 | 19 | Eagle Creek | EC Reach 1 | Instream and Floodplain Restoration | 0 | 0.5 | 0.5 | 5 | 5 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 2 | multiple target species spawning (possible steelhead) and rearing (Chinook lower 0.1 miles, steelhead, and bull trout) | 3 | Mostly process restoration to address root causes | 2 | Addresses bed and channel form | 7 | 1 | easy access, very little instream work, potential road decommissioning relatively inexpensive compared to typical restoration techniques | 7 | Moderate | Public ownership; road decommissioning impacts access for recreation, fire suppression, and other uses | Low | low potential for ameliorating impacts or increasing resilience
19 | 20 | LBC Project Area 7 | LBC reach 4a | Instream and Floodplain Restoration | 5.1 | 5.6 | 0.5 | 4 | 5 | 1 | moderate to high existing ecosystem function and habitat quality; moderate to high ecosystem function and habitat quality assuming all proposed actions implemented | 2 | moderate potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses instream structural and increased sediment quantity | 7 | 2 | moderately difficult access; limited instream work with hand felled or helicopter placed LWD | 3.5 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience
22 | 21 | South Creek | SC Reach 1 | Instream and Floodplain Restoration | 0 | 0.6 | 0.6 | 4 | 5 | 1 | moderate to high existing ecosystem function and habitat quality (downstream of RM 0.4); moderate to high ecosystem function and habitat quality assuming all project actions implemented | 2 | multiple target species spawning (steelhead; possibly Chinook lower 0.1 miles) and rearing (steelhead, Chinook, steelhead, and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses side channel and wetland habitat conditions, instream structural complexity, and bed and channel form | 7 | 2 | relatively easy access and typical restoration techniques | 3.5 | High | public ownership and no known feasibility issues | Low | low potential for ameliorating impacts or increasing resilience
30 | 22 | Introduced Species Management | UTR and LBC | Introduced Species Management | N/A | N/A | N/A | 3 | 5 | 2 | Implementing introduced species management has the potential to improve ecosystem function | 3 | for UTR and LBC, high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 1 | does not address physical processes root causes | 1 | addresses species interactions and primary productivity | 7 | 2 | moderate cost relative to instream restoration | 3.5 | Moderate | many challenges associated with species management | Low | introduced species management may increase salmon resilience
14 | 23 | LBC Project Area 2 | LBC Reach 2a | Road Improvements | 0.7 | 1 | 0.3 | 5 | 5 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 3 | high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 2 | High functioning existing conditions; partial restoration of root causes | 1 | addresses increased sediment quantity | 6 | 1 | easy access road drainage improvement; no instream or floodplain work | 6 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience
16 | 24 | LBC Project Area 4 | LBC Reach 2c | Instream and Floodplain Restoration | 1.7 | 2.1 | 0.4 | 5 | 5 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 3 | high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 2 | High functioning existing conditions; partial restoration of root causes | 1 | addresses increased sediment quantity | 6 | 1 | easy access road drainage improvement; no instream or floodplain work | 6 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience
29 | 25 | Instream Flow and Water Management | CC Reach 1 and LBC Reach 2 | Instream Flow and Water Management | N/A | N/A | N/A | 5 | 5 | 0 | Implementing instream flow and water management has the potential to improve ecosystem function and habitat quality modestly | 3 | for LBC, high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 1 | restoration of water quantity which is a relatively minor root cause in Little Bridge Creek | 2 | addresses water quantity | 6 | 1 | low cost due to relatively few existing diversions in Little Bridge Creek and Canyon Creek | 6 | Moderate | relatively few diversions (1 in Little Bridge Creek, and 2 in Canyon Creek) | High | increased instream flows can ameliorate temperate and increase salmon resilience
10 | 26 | UTR Project Area 10 | UTR Reach 4 | Instream and Floodplain Restoration | 26.5 | 27.2 | 0.7 | 5 | 5 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 3 | productive area for multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 2 | mix of process restoration and habitat enhancement | 1 | addresses instream structural complexity | 6 | 2 | moderately difficult access; relatively limited instream work and typical restoration techniques | 3 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience
20 | 27 | LBC Project Area 8 | LBC reach 4b | Instream and Floodplain Restoration | 5.6 | 6.8 | 1.2 | 4 | 5 | 1 | moderate to high existing ecosystem function and habitat quality; moderate to high ecosystem function and habitat quality assuming road decommissioning or abandonment | 2 | moderate potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 2 | mix of process restoration and habitat enhancement | 1 | addresses increased sediment quantity | 6 | 2 | easy access and limited instream work, moderate amount of road decommissioning and fill removal | 3 | Moderate | Public ownership; road decommissioning impacts access for recreation, fire suppression, and other uses | Low | low potential for ameliorating impacts or increasing resilience
7 | 28 | UTR Project Area 7 | UTR Reach 3b | Recreation Management | 24.2 | 24.5 | 0.3 | 6 | 6 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 3 | productive area for multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 1 | does not significantly address root causes | 1 | addresses riparian condition in the Poplar Flats Campground | 5 | 1 | easy access and relatively low cost | 5 | Moderate | Impacts the recreation use at Poplar Flats Campground | Low | low potential for ameliorating impacts or increasing resilience
12 | 29 | UTR Project Area 12 | UTR Reach 6 | Instream and Floodplain Restoration | 28.5 | 29.6 | 1.1 | 5 | 5 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 3 | highly productive areas from bull trout spawning; multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 1 | does not significantly address root causes | 1 | addresses instream structural complexity and increased sediment quantity | 5 | 2 | difficult access, limited instream work; LWD to be hand felled or helicopter placed | 2.5 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience
21 | 30 | North Creek | NC Reach 1 | Instream and Floodplain Restoration | 0 | 0.6 | 0.6 | 4 | 4 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 2 | Moderate potential for multiple target species; bull trout spawning; steelhead and bull trout rearing; Chinook rearing lower 0.2 miles | 1 | does not significantly address root causes | 1 | addresses increased sediment quantity | 4 | 1 | Easy access, limited restoration opportunities | 4 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience

## Prioritization UTR
Order | Project Information | [6 empty] | Benefit Score | [10 empty] | Cost Score |  | Cost Benefit | Feasibility Designation |  | Climate Change
| Rank | Project Name | Geomorphic Sub Reach | Project Type | Downstream RM | Upstream RM | Total Length (mi) | Restoration Gap Analysis |  |  |  | Existing and Potential Fish Use |  | Root Causes |  | Ecological Concerns |  | Total Benefit Score | Score (1-3) | Rationale/ Assumptions | Benefit to Cost Score | Feasibility Designation | Rationale/ Assumptions | Climate Change Designation | Rationale/Assumptions
[8 empty] | Existing Condition (1-7) | Achievable Target (1-7) | Final Gap Score Target - Existing (0-6) | Rationale/Assumptions | Score (1-3) | Rationale/Assumptions | Score (1-3) | Rationale/Assumptions | Score (1-3) | Rationale/Assumptions
2 | 1 | UTR Project Area 2 | UTR Reach 2a | Instream and Floodplain Restoration | 20.1 | 20.9 | 0.8 | 4 | 6 | 2 | moderate-to-high existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | productive area for multiple target species spawning (steelhead and Chinook) rearing (steelhead, Chinook and bull trout) | 3 | Mostly process restoration to address root causes | 3 | addresses side channel and wetland habitat conditions, instream structural complexity, bed and channel form, and riparian condition | 11 | 2 | relatively easy access and typical restoration techniques | 5.5 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
5 | 2 | UTR Project Area 5 | UTR Reach 2d | Instream and Floodplain Restoration | 22.4 | 22.7 | 0.3 | 4 | 6 | 2 | moderate-to-high existing ecosystem function and habitat quality; High ecosystem function and habitat quality assuming all proposed actions implemented | 3 | productive area for multiple target species spawning (steelhead and Chinook) rearing (steelhead, Chinook and bull trout) | 3 | Mostly process restoration to address root causes | 3 | addresses side channel and wetland habitat conditions, instream structural complexity, bed and channel form | 11 | 2 | moderately difficult access; relatively limited instream work and typical restoration techniques | 5.5 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
8 | 3 | UTR Project Area 8 | UTR Reach 3c | Instream and Floodplain Restoration | 24.8 | 25.5 | 0.7 | 5 | 6 | 1 | moderate-to-high existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | productive area for multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 3 | Mostly process restoration to address root causes | 3 | addresses side channel and wetland habitat conditions, instream structural complexity, bed and channel form | 10 | 2 | moderately difficult access; moderate instream work with typical restoration techniques | 5 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
11 | 4 | UTR Project Area 11 | UTR Reach 5 | Instream and Floodplain Restoration | 27.5 | 28 | 0.5 | 5 | 6 | 1 | moderate to high existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | productive area for multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 3 | Mostly process restoration to address root causes | 3 | addresses side channel and wetland habitat conditions, instream structural complexity, and bed and channel form | 10 | 2 | moderately difficult access; moderate amount of instream work with typical restoration techniques | 5 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
3 | 5 | UTR Project Area 3 | UTR Reach 2b | Instream and Floodplain Restoration | 20.9 | 21.6 | 0.7 | 4 | 6 | 2 | moderate-to-high existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | productive area for multiple target species spawning (steelhead and Chinook) rearing (steelhead, Chinook and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses side channel and wetland habitat conditions, instream structural complexity | 9 | 2 | moderately difficult access; relatively limited instream work and typical restoration techniques | 4.5 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
4 | 6 | UTR Project Area 4 | UTR Reach 2c | Instream and Floodplain Restoration | 21.8 | 22.2 | 0.4 | 4 | 6 | 2 | moderate-to-high existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming removal of all infrastructure in the floodplain | 3 | productive area for multiple target species spawning (steelhead and Chinook) rearing (steelhead, Chinook and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses instream structural complexity, bed and channel form | 9 | 2 | relatively easy access and typical restoration techniques; potential road decommissioning with low to moderate amount of floodplain fill removal | 4.5 | Moderate | public ownership; road decommissioning impacts access for recreation, fire suppression, and other uses | Low | low potential for ameliorating impacts or increasing resilience
9 | 7 | UTR Project Area 9 | UTR Reach 3d | Instream and Floodplain Restoration | 26 | 26.4 | 0.4 | 5 | 6 | 1 | moderate-to-high existing ecosystem function and habitat quality; High ecosystem function and habitat quality assuming removal of all infrastructure in the floodplain | 3 | productive area for multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 2 | mix of process restoration and habitat enhancement | 3 | addresses side channel and wetland habitat conditions, instream structural complexity, bed and channel form, riparian condition, and increased sediment quantity | 9 | 2 | easy access, moderate amount of instream work; come alternatives to realign road could increase to high cost | 4.5 | Moderate | public ownership; proposed actions may impact recreational areas | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
1 | 8 | UTR Project Area 1 | UTR Reach 1 | Instream and Floodplain Restoration | 17.8 | 18.2 | 0.4 | 5 | 6 | 1 | moderate-to-high existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming removal of all infrastructure in the floodplain | 3 | highly productive area for multiple target species spawning (steelhead and Chinook) rearing (steelhead, Chinook and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses side channel and wetland habitat conditions instream structural complexity | 8 | 2 | easy access, relatively limited instream work; potential road decommissioning with moderate amount of floodplain fill removal | 4 | Moderate | Public ownership; road decommissioning impacts access for recreation, fire suppression, and other uses | Low | floodplain fill removal would improve side channel habitat but low potential for ameliorating impacts or increasing resilience
6 | 9 | UTR Project Area 6 | UTR Reach 3a | Instream and Floodplain Restoration | 23.5 | 23.7 | 0.2 | 5 | 6 | 1 | moderate-to-high existing ecosystem function and habitat quality; high ecosystem function assuming all proposed actions implemented | 3 | productive area for multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses side channel and wetland habitat conditions, instream structural complexity | 8 | 2 | moderately difficult access; relatively limited instream work and typical restoration techniques | 4 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels, wetland, and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
13 | 10 | Introduced Species Management | UTR and LBC | Introduced Species Management | N/A | N/A | N/A | 3 | 5 | 2 | Implementing introduced species management has the potential to improve ecosystem function | 3 | for UTR and LBC, high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 1 | does not address physical processes root causes | 1 | addresses species interactions and primary productivity | 7 | 2 | moderate cost relative to instream restoration | 3.5 | Moderate | many challenges associated with species management | Low | introduced species management may increase salmon resilience
10 | 11 | UTR Project Area 10 | UTR Reach 4 | Instream and Floodplain Restoration | 26.5 | 27.2 | 0.7 | 5 | 5 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 3 | productive area for multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 2 | mix of process restoration and habitat enhancement | 1 | addresses instream structural complexity | 6 | 2 | moderately difficult access; relatively limited instream work and typical restoration techniques | 3 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience
7 | 12 | UTR Project Area 7 | UTR Reach 3b | Recreation Management | 24.2 | 24.5 | 0.3 | 6 | 6 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 3 | productive area for multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 1 | does not significantly address root causes | 1 | addresses riparian condition in the Poplar Flats Campground | 5 | 1 | easy access and relatively low cost | 5 | Moderate | Impacts the recreation use at Poplar Flats Campground | Low | low potential for ameliorating impacts or increasing resilience
12 | 13 | UTR Project Area 12 | UTR Reach 6 | Instream and Floodplain Restoration | 28.5 | 29.6 | 1.1 | 5 | 5 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 3 | highly productive areas from bull trout spawning; multiple target species spawning and rearing (steelhead, Chinook and bull trout) | 1 | does not significantly address root causes | 1 | addresses instream structural complexity and increased sediment quantity | 5 | 2 | difficult access, limited instream work; LWD to be hand felled or helicopter placed | 2.5 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience

## Prioritization LBC
Order | Project Information | [6 empty] | Benefit Score | [10 empty] | Cost Score |  | Cost Benefit | Feasibility Designation |  | Climate Change
| Rank | Project Name | Geomorphic Sub Reach | Project Type | Downstream RM | Upstream RM | Total Length (mi) | Restoration Gap Analysis |  |  |  | Existing and Potential Fish Use |  | Root Causes |  | Ecological Concerns |  | Total Benefit Score | Score (1-3) | Rationale/ Assumptions | Benefit to Cost Score | Feasibility Designation | Rationale/ Assumptions | Climate Change Designation | Rationale/Assumptions
[8 empty] | Existing Condition (1-7) | Achievable Target (1-7) | Final Gap Score Target - Existing (0-6) | Rationale/Assumptions | Score (1-3) | Rationale/Assumptions | Score (1-3) | Rationale/Assumptions | Score (1-3) | Rationale/Assumptions
6 | 1 | LBC Project Area 6 | LBC reach 3 | Instream and Floodplain Restoration | 3 | 5.1 | 2.1 | 3 | 6 | 3 | moderate existing ecosystem function and habitat quality; high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 3 | Mostly process restoration to address root causes | 3 | addresses side channel and wetland habitat conditions, instream structural complexity, and bed and channel form and riparian condition; actions to increase floodplain groundwater storage may modestly address water quantity and temperature | 12 | 2 | relatively easy access and typical restoration techniques | 6 | High | public ownership, no know issues limiting project feasibility | High | side channels, alcoves, wetland and riparian restoration can ameliorate temperate and peak flow increases and increase salmon resilience
9 | 2 | Beaver Management | LBC Reaches 2 and 3 | Beaver Management | 0.7 | 5.1 | 4.4 | 3 | 5 | 2 | low to moderate current conditions, moderate to high recovery potential | 3 | high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 3 | process restoration addressing root causes (beaver extirpation) | 3 | addresses water quantity, water temperature, side channel and wetland habitat conditions | 11 | 1 | relatively low cost, availability for volunteer labor | 11 | High | Mostly public land ownership; existing programs in the subbasin for reintroducing beavers | High | beaver activity can ameliorate temperate and peak flow increases and increase salmon resilience
1 | 3 | LBC Project Area 1 | LBC Reach 1 | Instream and Floodplain Restoration | 0 | 0.7 | 0.7 | 2 | 5 | 3 | low existing ecosystem function and habitat quality; moderate to high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | moderate to high potential productivity multiple target species spawning and rearing (steelhead and bull trout); Chinook rearing near mouth | 2 | mix of process restoration and habitat enhancement | 2 | addresses instream structural complexity, bed and channel form, riparian condition, and increased sediment quantity | 10 | 2 | easy to moderately difficult access and moderate amount of instream work with typical restoration techniques | 5 | Moderate | multiple private landowners affected (lower 0.2 miles), their willingness is unknown | Low | low potential for ameliorating impacts or increasing resilience
5 | 4 | LBC Project Area 5 | LBC Reach 2d | Instream and Floodplain Restoration | 2.1 | 3 | 0.9 | 3 | 5 | 2 | moderate existing ecosystem function and habitat quality; moderate to high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | high potential productivity multiple target species spawning and rearing (steelhead and bull trout)mouth | 2 | mix of process restoration and habitat enhancement | 2 | addresses side channel and wetland habitat conditions, instream structural complexity, and bed and channel form, and riparian condition | 9 | 2 | relatively easy access, relatively limited instream work and typical restoration techniques | 4.5 | High | public ownership, no know issues limiting project feasibility | Moderate | moderate potential to enhance side channels and riparian restoration which can ameliorate temperate and peak flow increases and increase salmon resilience
3 | 5 | LBC Project Area 3 | LBC Reach 2b | Instream and Floodplain Restoration | 1 | 1.7 | 0.7 | 4 | 5 | 1 | moderate to high existing ecosystem function and habitat quality; moderate to high ecosystem function and habitat quality assuming all proposed actions implemented | 3 | high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses instream structural complexity, riparian condition, and increased sediment quantity | 8 | 2 | moderately difficult access; relatively limited instream work and typical restoration techniques | 4 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience
10 | 6 | Land Acquisition | CC Reach 1 and LBC Reach 1 | Land Acquisition | N/A | N/A | N/A | 3 | 5 | 2 | Implementing introduced species management has the potential to improve ecosystem function and habitat quality | 3 | for LBC, high potential productivity multiple target species spawning and rearing (steelhead and bull trout); Chinook rearing near mouth | 2 | partial restoration of root causes (land use impacts) | 1 | does not directly address limiting factors | 8 | 2 | moderate cost relative to instream restoration; could be low cost if not all parcels are purchased | 4 | Moderate | moderate feasibility due to unknown landowner willingness | Low | low potential for ameliorating impacts or increasing resilience
7 | 7 | LBC Project Area 7 | LBC reach 4a | Instream and Floodplain Restoration | 5.1 | 5.6 | 0.5 | 4 | 5 | 1 | moderate to high existing ecosystem function and habitat quality; moderate to high ecosystem function and habitat quality assuming all proposed actions implemented | 2 | moderate potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses instream structural and increased sediment quantity | 7 | 2 | moderately difficult access; limited instream work with hand felled or helicopter placed LWD | 3.5 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience
11 | 8 | Introduced Species Management | UTR and LBC | Introduced Species Management | N/A | N/A | N/A | 3 | 5 | 2 | Implementing introduced species management has the potential to improve ecosystem function | 3 | for UTR and LBC, high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 1 | does not address physical processes root causes | 1 | addresses species interactions and primary productivity | 7 | 2 | moderate cost relative to instream restoration | 3.5 | Moderate | many challenges associated with species management | Low | introduced species management may increase salmon resilience
2 | 9 | LBC Project Area 2 | LBC Reach 2a | Road Improvements | 0.7 | 1 | 0.3 | 5 | 5 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 3 | high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 2 | High functioning existing conditions; partial restoration of root causes | 1 | addresses increased sediment quantity | 6 | 1 | easy access road drainage improvement; no instream or floodplain work | 6 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience
4 | 10 | LBC Project Area 4 | LBC Reach 2c | Instream and Floodplain Restoration | 1.7 | 2.1 | 0.4 | 5 | 5 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 3 | high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 2 | High functioning existing conditions; partial restoration of root causes | 1 | addresses increased sediment quantity | 6 | 1 | easy access road drainage improvement; no instream or floodplain work | 6 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience
12 | 11 | Instream Flow and Water Management | CC Reach 1 and LBC Reach 2 | Instream Flow and Water Management | N/A | N/A | N/A | 5 | 5 | 0 | Implementing instream flow and water management has the potential to improve ecosystem function and habitat quality modestly | 3 | for LBC, high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 1 | restoration of water quantity which is a relatively minor root cause in Little Bridge Creek | 2 | addresses water quantity | 6 | 1 | low cost due to relatively few existing diversions in Little Bridge Creek and Canyon Creek | 6 | Moderate | relatively few diversions (1 in Little Bridge Creek, and 2 in Canyon Creek) | Moderate | increased instream flows can ameliorate temperate and increase salmon resilience
8 | 12 | LBC Project Area 8 | LBC reach 4b | Instream and Floodplain Restoration | 5.6 | 6.8 | 1.2 | 4 | 5 | 1 | moderate to high existing ecosystem function and habitat quality; moderate to high ecosystem function and habitat quality assuming road decommissioning or abandonment | 2 | moderate potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 2 | mix of process restoration and habitat enhancement | 1 | addresses increased sediment quantity | 6 | 2 | easy access and limited instream work, moderate amount of road decommissioning and fill removal | 3 | Moderate | Public ownership; road decommissioning impacts access for recreation, fire suppression, and other uses | Low | low potential for ameliorating impacts or increasing resilience

## Prioritization Tributaries
Order | Project Information | [6 empty] | Benefit Score | [10 empty] | Cost Score |  | Cost Benefit | Feasibility Designation |  | Climate Change
| Rank | Project Name | Geomorphic Sub Reach | Project Type | Downstream RM | Upstream RM | Total Length (mi) | Restoration Gap Analysis |  |  |  | Existing and Potential Fish Use |  | Root Causes |  | Ecological Concerns |  | Total Benefit Score | Score (1-3) | Rationale/ Assumptions | Benefit to Cost Score | Feasibility Designation | Rationale/ Assumptions | Climate Change Designation | Rationale/Assumptions
[8 empty] | Existing Condition (1-7) | Achievable Target (1-7) | Final Gap Score Target - Existing (0-6) | Rationale/Assumptions | Score (1-3) | Rationale/Assumptions | Score (1-3) | Rationale/Assumptions | Score (1-3) | Rationale/Assumptions
6 | 1 | Canyon Creek | CC Reach 1 | Instream and Floodplain Restoration | 0 | 0.4 | 0.4 | 2 | 4 | 2 | low existing ecosystem function and habitat quality; moderate to high ecosystem function and habitat quality assuming all proposed actions implemented | 1 | potential for steelhead rearing; barrier currently blocks upstream migration | 3 | Mostly process restoration to address root causes | 2 | addresses instream structural complexity, riparian condition, and increased sediment quantity | 8 | 2 | Easy access and minimal instream work; relatively high cost for the Twisp River road crossing | 4 | Moderate | multiple private landowners affected (lower 0.2 miles), their willingness is unknown | Low | low potential for ameliorating impacts or increasing resilience
4 | 2 | War Creek | WC Reach 1 | Instream and Floodplain Restoration | 0.3 | 1.3 | 1 | 4 | 5 | 1 | moderate to high existing ecosystem function and habitat quality (downstream of RM 0.3 to 0.7); moderate to high ecosystem function and habitat quality assuming all project actions implemented | 2 | multiple target species spawning (possible steelhead; possible Chinook lower 0.2 miles) and rearing (Chinook lower 0.3 miles, steelhead, and bull trout) | 3 | Mostly process restoration to address root causes | 2 | Addresses bed and channel form | 8 | 2 | easy access, relatively little instream work and typical restoration techniques | 4 | Moderate | Public ownership; road decommissioning impacts access for recreation, fire suppression, and other uses | Low | low potential for ameliorating impacts or increasing resilience
7 | 3 | Land Acquisition | CC Reach 1 and LBC Reach 1 | Land Acquisition | N/A | N/A | N/A | 3 | 5 | 2 | Implementing introduced species management has the potential to improve ecosystem function and habitat quality | 3 | for LBC, high potential productivity multiple target species spawning and rearing (steelhead and bull trout); Chinook rearing near mouth | 2 | partial restoration of root causes (land use impacts) | 1 | does not directly address limiting factors | 8 | 2 | moderate cost relative to instream restoration; could be low cost if not all parcels are purchased | 4 | Moderate | moderate feasibility due to unknown landowner willingness | Low | low potential for ameliorating impacts or increasing resilience
3 | 4 | Reynolds Creek | RC Reach 1 | Instream and Floodplain Restoration | 0 | 0.6 | 0.6 | 4 | 4 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 2 | multiple target species spawning (bull trout) and rearing (possibly Chinook, steelhead, and bull trout) | 3 | Mostly process restoration to address root causes | 2 | Addresses bed and channel form | 7 | 1 | easy access, no instream work, potential road decommissioning relatively inexpensive compared to typical restoration techniques | 7 | Moderate | Public ownership; road decommissioning impacts access for recreation, fire suppression, and other uses | Low | low potential for ameliorating impacts and increasing resilience
5 | 5 | Eagle Creek | EC Reach 1 | Instream and Floodplain Restoration | 0 | 0.5 | 0.5 | 5 | 5 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 2 | multiple target species spawning (possible steelhead) and rearing (Chinook lower 0.1 miles, steelhead, and bull trout) | 3 | Mostly process restoration to address root causes | 2 | Addresses bed and channel form | 7 | 1 | easy access, very little instream work, potential road decommissioning relatively inexpensive compared to typical restoration techniques | 7 | Moderate | Public ownership; road decommissioning impacts access for recreation, fire suppression, and other uses | Low | low potential for ameliorating impacts or increasing resilience
2 | 6 | South Creek | SC Reach 1 | Instream and Floodplain Restoration | 0 | 0.6 | 0.6 | 4 | 5 | 1 | moderate to high existing ecosystem function and habitat quality (downstream of RM 0.4); moderate to high ecosystem function and habitat quality assuming all project actions implemented | 2 | multiple target species spawning (steelhead; possibly Chinook lower 0.1 miles) and rearing (steelhead, Chinook, steelhead, and bull trout) | 2 | mix of process restoration and habitat enhancement | 2 | addresses side channel and wetland habitat conditions, instream structural complexity, and bed and channel form | 7 | 2 | relatively easy access and typical restoration techniques | 3.5 | High | public ownership and no known feasibility issues | Low | low potential for ameliorating impacts or increasing resilience
8 | 7 | Instream Flow and Water Management | CC Reach 1 and LBC Reach 2 | Instream Flow and Water Management | N/A | N/A | N/A | 5 | 5 | 0 | Implementing instream flow and water management has the potential to improve ecosystem function and habitat quality modestly | 3 | for LBC, high potential productivity multiple target species spawning and rearing (steelhead and bull trout) | 1 | restoration of water quantity which is a relatively minor root cause in Little Bridge Creek | 2 | addresses water quantity | 6 | 1 | low cost due to relatively few existing diversions in Little Bridge Creek and Canyon Creek | 6 | Moderate | relatively few diversions (1 in Little Bridge Creek, and 2 in Canyon Creek) | Moderate | increased instream flows can ameliorate temperate and increase salmon resilience
1 | 8 | North Creek | NC Reach 1 | Instream and Floodplain Restoration | 0 | 0.6 | 0.6 | 4 | 4 | 0 | Implementing proposed actions have the potential to improve ecosystem function and habitat quality modestly | 2 | Moderate potential for multiple target species; bull trout spawning; steelhead and bull trout rearing; Chinook rearing lower 0.2 miles | 1 | does not significantly address root causes | 1 | addresses increased sediment quantity | 4 | 1 | Easy access, limited restoration opportunities | 4 | High | public ownership, no know issues limiting project feasibility | Low | low potential for ameliorating impacts or increasing resilience

## Periodicity Charts
Twisp River Fish Periodicity: TR-1, RM 17.8 to 22.7 (at Reynolds Creek)
| Species | Lifestage | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sept | Oct | Nov | Dec
| Spring Chinook Salmon | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Summer Steelhead | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Bull Trout | Adult Immigration/Emigration
Adult Spawning
Incubation/Emergence
Juvenile Rearing
No. Life stages |  | Juvenile Emigration
13
Twisp River Fish Periodicity: TR-2, RM 22.7 to RM 29.6 at falls
| Species | Lifestage | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sept | Oct | Nov | Dec
| Spring Chinook Salmon | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Summer Steelhead | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Bull Trout | Adult Immigration/Emigration
Adult Spawning
Incubation/Emergence
Juvenile Rearing
No. Life stages |  | Juvenile Emigration
15
Twisp River Fish Periodicity: NC, North Creek, RM 0.0 to RM 0.6 (at falls)
| Species | Lifestage | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sept | Oct | Nov | Dec
| Spring Chinook Salmon | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Summer Steelhead | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
|  | Juvenile Rearing | [12 empty] | ?
Juvenile Emigration
| Bull Trout | Adult Immigration/Emigration
Adult Spawning
Incubation/Emergence
Juvenile Rearing
No. Life stages |  | Juvenile Emigration
8
Twisp River Fish Periodicity: SC, South Creek, RM 0.0 to RM 0.6 (at falls)
| Species | Lifestage | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sept | Oct | Nov | Dec
| Spring Chinook Salmon | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Summer Steelhead | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Bull Trout | Adult Immigration/Emigration
|  | Adult Spawning | [8 empty] | ? | ?
Incubation/Emergence
Juvenile Rearing
No. Life stages |  | Juvenile Emigration
9
Twisp River Fish Periodicity: RC, Reynolds Creek, RM 0.0 to RM 0.6 (at falls)
| Species | Lifestage | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sept | Oct | Nov | Dec
| Spring Chinook Salmon | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
|  | Juvenile Rearing | [12 empty] | ?
Juvenile Emigration
| Summer Steelhead | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Bull Trout | Adult Immigration/Emigration
Adult Spawning
Incubation/Emergence
Juvenile Rearing
No. Life stages |  | Juvenile Emigration
6
Twisp River Fish Periodicity: WEC, War & Eagle Creeks, RM 0.0 to Passage Barriers
| Species | Lifestage | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sept | Oct | Nov | Dec
| Spring Chinook Salmon | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Summer Steelhead | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Bull Trout | Adult Immigration/Emigration
Adult Spawning
Incubation/Emergence
Juvenile Rearing
No. Life stages |  | Juvenile Emigration
5
Twisp River Fish Periodicity: CC, Canyon Creek, RM 0.0 to headwaters
| Species | Lifestage | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sept | Oct | Nov | Dec
| Spring Chinook Salmon | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Summer Steelhead | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Bull Trout | Adult Immigration/Emigration
Adult Spawning
Incubation/Emergence
Juvenile Rearing
No. Life stages |  | Juvenile Emigration
2
Twisp River Fish Periodicity: LBC, Little Bridge Creek, RM 0.0 to headwaters
| Species | Lifestage | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sept | Oct | Nov | Dec
| Spring Chinook Salmon | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Summer Steelhead | Adult Immigration & Holding
Adult Spawning
Incubation/Emergence
Juvenile Rearing
Juvenile Emigration
| Bull Trout | Adult Immigration/Emigration
Adult Spawning
Incubation/Emergence
Juvenile Rearing
No. Life stages |  | Juvenile Emigration
11

## Ecological Concerns
The revised Biological Strategy seven ecological concerns for the upper Twisp River assessment unit, in priority order (UCRTT 2014)
Upper Twisp River Assessment Unit
1) peripheral and transitional habitats (side channel and wetland habitat conditions)
2) channel structure and form (instream structural complexity)
3) channel structure and form (bed and channel form)
4) riparian condition (riparian condition and large wood recruitment)
5) food (altered primary productivity or prey species competition and diversity)
6) sediment (increased sediment quantity)
7) species interactions (introduced competitors and predators)
High Priority
Moderate Priority
Low Priority
proposed actions enhance side channel and wetland habitat conditions, increase instream structural complexity, imporve bed and channel form
Lower Twisp River Assessment Unit (Includes Little Bridge Creek)
1) Water Quantity (Decreased Water Quantity)
2) Water Quality (Temperature)
3) Channel Structure and Form (Bed and Channel Form)
4) Peripheral and Transitional Habitats (Side channel and Wetland Habitat Conditions)
5) Channel Structure and Form (Instream Structural Complexity)
6) Riparian Condition (Riparian Condition)
7) Sediment (Increased Sediment Quantity)
8) Food (Altered Primary Productivity)
9) Species Interactions (Introduced Competitors and Predators)
High Priority
Moderate Priority
Low Priority

## Climate
Restoration Actions Table |  | Climate Change Variables and Values (based on Beechie, et. al., 2013)
|  | Ameliorates Temperature Increase | Value | Ameliorates Base Flow Decrease | Value | Ameliorates Peak Flow Increase | Value | Increases Salmon Resilience | Value
Land and Water Preservation:
1 | Protection: (Acquisitions, Easements, Cooperative Agreements) | Full Moon |  | Full Moon |  | Full Moon |  | Full Moon
2 | Land Management: (Grazing Plans, Fire management, etc.) | Full Moon |  | Full Moon |  | Full Moon |  | Full Moon
Water Quality Improvements:
3 | Reduce - Mitigate Point or Non-Point Source Impacts | No Impacts |  | No Impacts |  | No Impacts |  | Full Moon
4 | Nutrients Additions (carcasses) | No Impacts |  | No Impacts |  | No Impacts |  | Half Moon
5 | Upland Vegetation Treatment - Management | No Impacts |  | Half Moon |  | Half Moon |  | No Impacts
Sediment Reduction:
6 | Road Grading - Drainage Improvements | No Impacts |  | No Impacts |  | Full Moon |  | No Impacts
7 | Road Decommissioning or Abandonment | No Impacts |  | No Impacts |  | Full Moon |  | No Impacts
Water Quantity:
8 | Water Management-Improve Irrigation Efficiency | Half Moon |  | Full Moon |  | No Impacts |  | Half Moon
9 | Acquire or Increase Instream Flow (Lease/Purchase; GW Storage) | Full Moon |  | Full Moon |  | No Impacts |  | Full Moon
Riparian Restoration and Management:
10 | Remove Non-native Plants | Half Moon |  | Half Moon |  | No Impacts |  | No Impacts
11 | Off--Site Water Developments | No Impacts |  | No Impacts |  | No Impacts |  | No Impacts
12 | Riparian Buffer Strip, Planting | Full Moon |  | Half Moon |  | No Impacts |  | Half Moon
13 | Selective Thinning | No Impacts |  | No Impacts |  | No Impacts |  | No Impacts
14 | Beaver Re-introduction or Management | Full Moon |  | Full Moon |  | Full Moon |  | Full Moon
15 | Riparian Fencing | Full Moon |  | Half Moon |  | Half Moon |  | Full Moon
Bank Restoration or Modification
16 | Bank Shaping and Stabilization | Half Moon |  | No Impacts |  | No Impacts |  | Half Moon
17 | Removal of Bank Armoring | Half Moon |  | No Impacts |  | No Impacts |  | Full Moon
18 | Restore Banklines with LWD - Bioengineering | Full Moon |  | Full Moon |  | Full Moon |  | Full Moon
Instream Structures and Habitat Complexity:
19 | Boulder Placements | No Impacts |  | No Impacts |  | No Impacts |  | Half Moon
20 | LWD Placements - Individual Pieces, Whole Trees, Logjams, etc. | Half Moon |  | No Impacts |  | No Impacts |  | Half Moon
21 | Weirs for Grade Control | Half Moon |  | Half Moon |  | Half Moon |  | No Impacts
Floodplain Reconnection:
22 | Levee Modifications: Removal, Setback, Breach | Full Moon |  | No Impacts |  | Full Moon |  | Full Moon
23 | Remove and/or Relocate Floodplain Infrastructure | Full Moon |  | No Impacts |  | Full Moon |  | Full Moon
24 | Restoration of Floodplain Topography and Vegetation | Full Moon |  | No Impacts |  | Full Moon |  | Full Moon
25 | Floodplain Excavation: Benching | Half Moon |  | No Impacts |  | No Impacts |  | Half Moon
Side Channel / Off-Channel Habitat Restoration:
26 | Improve Thermal Refugia (cold spring reconnect, winter temps) | Full Moon |  | No Impacts |  | No Impacts |  | Full Moon
27 | Perennial Side Channel | Full Moon |  | Half Moon |  | Full Moon |  | Full Moon
28 | Secondary Channel (non-perennial) | Full Moon |  | No Impacts |  | Full Moon |  | Full Moon
29 | Floodplain Pond | Half Moon |  | Half Moon |  | Half Moon |  | Half Moon
30 | Wetland | Full Moon |  | Half Moon |  | Half Moon |  | Full Moon
31 | Alcove | Half Moon |  | No Impacts |  | Half Moon |  | Full Moon
32 | Hyporheic Off-Channel Habitat (Groundwater) | Full Moon |  | Half Moon |  | No Impacts |  | Full Moon
Stream Channel Modifications:
33 | Spawning Gravel Cleaning and Placement | No Impacts |  | No Impacts |  | No Impacts |  | No Impacts
34 | Pool Construction | Half Moon |  | No Impacts |  | No Impacts |  | Half Moon
35 | Riffle Construction | No Impacts |  | No Impacts |  | No Impacts |  | No Impacts
36 | Meander (Oxbow) Re-connect - Reconstruction | Full Moon |  | Half Moon |  | Half Moon |  | Full Moon
37 | Channel Reconstruction | Full Moon |  | Half Moon |  | Half Moon |  | Full Moon
Fish Passage Restoration:
38 | Structural Passage (Diversions, Screening) | No Impacts |  | No Impacts |  | No Impacts |  | Full Moon
39 | Barrier or Culvert Replacement or Removal | No Impacts |  | No Impacts |  | No Impacts |  | Full Moon
40 | Dam Removal or Breaching | Full Moon |  | Full Moon |  | No Impacts |  | Full Moon
Resilience = the ability of a system to absorb change and still maintain its basic ecosystem functions and relationships, even though the balance of habitat types or species may shift slowly through time .
Filled circles indicate positive effect
Half circles indicate context-dependent effects.
Empty cells indicate no effect

## Methods
Project Ranking Methods (Version: June 2017)
Step 1: Benefit Score Projects are scored according to 4 benefit categories, which include a
“recovery gap” category and 3 additional categories. Scores for each category are summed to obtain the Benefit Score.
Step 2: Cost Score Projects are given a Cost Score, which reflects the overall relative cost for the project based on techniques, access, and construction feasibility issues.
Step 3: Benefit-to-Cost Score Total benefit score (sum of all 4 benefit scores) is divided by
the cost score to obtain the Benefit-to-Cost Score.
Step 4: Feasibility Designation Projects are given a Feasibility Designation based on the
overall likely feasibility of being able to implement the project within a 10-year timeframe.
Benefit Score
The Benefit Score includes the summation of scores from 4 categories. These include the Recovery Gap score (0-6 points), the Fish Use score (1-3 points), the Root Causes score (1-3
points), Ecological Concerns Score (1-3). The guidelines for scoring are provided below.
Recovery Gap
Existing Condition Rating (1-7)
1 – Very low ecosystem function and habitat quality. Highly altered systems.
2 – Low ecosystem function and habitat quality.
3 – Low-to-moderate ecosystem function and habitat quality.
4 – Moderate ecosystem function and habitat quality.
5 – Moderate-to-high ecosystem function and habitat quality.
6 – High ecosystem function and habitat quality.
7 – Very high level of natural ecosystem function and habitat quality. Pristine, unaltered systems.
Achievable Condition Rating (1-7)
These ratings use the same categories as above but reflect the future potential recovery trajectory.
This is a rating of what can realistically be achieved given past and on-going impacts and constraints of land use, infrastructure, social acceptance, and ownership. Ratings should reflect an “optimistic potential scenario”
in order to not discount large potential changes.
Final Gap Score (0-6)
This is simply the achievable condition rating minus the existing condition rating. This represents the gap that can be filled between existing and target conditions through restoration measures.
Fish Use
3 – High existing or potential productivity area for spawning or rearing for multiple species
2 – Moderate existing or potential productivity area for one or more species
1 – Low existing or potential productivity area for one or two species
Root Causes
3 – Restoration of root causes and key physical processes that create and maintain habitat over time
2 – Partial restoration of root causes
1 – Primarily a structurally-focused restoration strategy that doesn’t significantly address underlying causes
Ecological Concerns Score
3 – Addresses multiple high priority ecological concerns (UCRTT 2014)
2 – Addresses one or more moderate priority ecological concerns and/or one high priority ecological concern (UCRTT 2014)
1 – Addresses only low priority ecological concerns (UCRTT 2014)
Cost Score
The cost score reflects the relative cost for the project based on techniques, access, and feasibility issues. This is a relative cost, not an absolute cost, so the scale of the project is NOT
factored into this score. The cost score ranges from 1 to 3, with 1 reflecting relatively lower cost
projects. The following guidelines/examples can help to determine the cost score.
3 – High relative cost
· Uses high cost techniques (e.g. constructed banks, highly engineered log jams, extensive channel shaping, extensive infiltration galleries)
· Deep excavation or long distance hauling of spoils
· Entails construction of additional new flood control or bank erosion features (e.g. setback levees or buried rip-rap)
· Extensive planting or invasive weed control
· Limited, difficult, or remote access
· Intensive de-watering requirements
2 – Moderate relative cost
· Uses moderate cost techniques (e.g. typical log jam structures)
· Moderate excavation and hauling distance of spoils
· Typical planting or invasive weed control
· Moderate access conditions
· Standard or no de-watering requirements
1 – Low relative cost
· Uses low cost techniques (e.g. non-ballasted log placements)
· Minimal excavation and hauling distance of spoils
· Little to no planting or weed control
· Easy access conditions
· No de-watering required
· Availability of free materials or volunteer labor
Benefit-to-Cost Score
The benefit-to-cost score is simply the benefit score divided by the cost score. This is a relative
value used to compare project benefits.
Feasibility Designation
The feasibility designation is the overall likely feasibility of being able to implement the project
within a 10-year timeframe. This is based on landownership, as well as economic, regulatory,
political, social, permitting, or other considerations that are known to impact the feasibility of conducting projects within a reasonable timeframe.
The feasibility designation is not used as part of the project scoring because feasibility issues may change over time and it is desirable to evaluate project benefits independent of feasibility. The designations include the following:
High feasibility
· No known feasibility issues.
· One or two landowners; or landowner(s) has already indicated willingness
Moderate feasibility
· There are potential feasibility constraints that could affect the likelihood of project implementation within a 10-year timeframe
· Three to five landowners; or there is reason to believe landowner(s) would grant permission
Unlikely feasibility
· There are known feasibility constraints that would be expected to limit the ability to implement the project within a 10-year timeframe
· More than five landowners: or there is reason to believe landowner(s) would not grant permission
Climate Change Impact Designation
High potential for ameliorating impacts and increasing salmon resilience based on Beechie et al. (2013)
Moderate potential for ameliorating impacts and increasing salmon resilience based on Beechie et al. (2013)
Low potential for ameliorating impacts and increasing salmon resilience based on Beechie et al. (2013)
References
Beechie, T., H. Imaki, J. Greene, A. Wade, H. Wu, G. Pess, P. Roni, J. Kimball, J. Stanford, P. Kiffney, and N. Mantua. 2013. Restoring Salmon Habitat for a Changing Climate. River Res. Applic. 29: 939–960.
UCRTT. 2014. A biological strategy to protect and restore salmonid habitat in the Upper Columbia Region. Prepared for the Upper Columbia Salmon Recovery Board. 44 pp. and appendices.